## User_Stories
|  | ID | Story Title | Depends On | Points | Priority | As a/an [user type] | I want [functionality] | So that [value] | NFR | Definition of Done | Epic ID | Notes | Status
|  | S0 | Example |  | 1 | Medium | Professor | to create requirements | my students understand. | Understandability | When students grok! | 0 |  | Open
rest of the IDs :(
|  |  | Create User |  | 2 | High | Player | to create an account | I can play the game |  | when I am able to create a new account |  |  | Open
|  |  | Guest account |  | 1 | High | Player | to play as guest | I can play without registering |  | able to play successfully without registering |  |  | Open
|  |  | Login | Create User | 1 | High | Player | to log in to my account | I can access my saved data |  | when I am able to access my previously created account |  |  | Open
|  |  | Logout | Login | 1 | High | Player | to log out of my account | Only I have access to my account |  | when I am able to control access to my account |  |  | Open
| !SR |  | Recovery |  | 2 | High | Player | to reset my password | I can recover my account |  | when I am able to recover my account |  |  | Open
|  |  | Password |  | 2 | High | Player | to change my password | I can secure my account |  | when I am able to secure my accoung |  |  | Open
|  |  | Update |  | 1 | Low/Med | Player | to update personal information | I have an accurate profile |  | when I am able to update my account |  |  | Open
|  |  | Profile Avatar |  | 2 | Low/Med | Player | to create an avatar (profile picture) | I can show off my creativity |  | when I am able to choose a profile picture |  |  | Open
|  |  | Add Friend |  | 2 | High | Player | to add another player as a friend | I can fascilitate playing with friends |  | when I am able to add another player to my list of friends |  |  | Open
| !SR? How is this different from add friend? |  | Find Friend | Add Friend | 3 | High | Player | to search for other players by name | I can add friends that I know |  | when I am able to search for users |  |  | Open
|  |  | Remove Friend |  | 2 | High | Player | to remove another player as a friend | I can shorten my friends list |  | when I am able to remove another player from my list of friends |  |  | Open
|  |  | Show Friends |  | 1 | Med | Player | to see my list of friends | I know who my friends are |  | when I am able to see all the players in my friends list
| why 3 points? |  | Invite Friend |  | 3 | HIgh | Player | to invite a friend to my table | I can play at the same table with my friends |  | when I am able to invite another player to my table |  |  | Open
|  |  | Display Stats |  | 1 | Low | Player | to show off my stats (W/L) | I can compare with my friends |  | when I can compare stats |  |  | Open
|  |  | Report player |  | 2 | Medium | Player | to report another player for violations | I can ensure players are following rules/guidelines |  | when I am able to report a player
|  |  | Public Chat |  | 5 | High | Player | to send messages to the entire table | I can communicate publicly |  | I can communicate with the table |  | Email-Like | Open
R8 | collectively 10 points is a lot for these two |  | Private Chat |  | 5 | High | Player | to send messages to my friends | we can communicate outside of the table-chat/game-chat |  | I can communicate privately |  | Email-Like | Open
|  |  | Review Chat | Private Chat | 2 | Low | Player | to view previous messages | review my conversations |  | Private chats are saved |  | No point in saving public chats | Open
R8 | why 8 points? |  | Lobby |  | 8 | High | Player | Access the lobby | I can see live tables, see open/closed tables, sort by amount of tables |  | Able to access lobby correctly |  |  | Open
| rethink "as a player I want to give all users …." |  | Tutorial |  | 3 | High | Player | to give all users option for tutorial | Can learn to play the game |  | Users understand game |  |  | Open
|  |  | Table |  | 5 | High | Player | to start my own table | I can play with friends or Random people |  | My friends or randoms can join my table |  |  | Open
| this is part of the table story from row 30 |  | Table Password | Table | 1 | Med/High | Player | Only my friends to join the table | Only my friends can join my table |  | My friends can join my table |  |  | Open
| this is part of the table story from row 30 |  | Table Currency | Table | 1 | High | Player | To set the currency to join the table | I can have high and low stakes games |  | Can set currency for table |  |  | Open
| the client want this. Its an NFR |  | Ads |  | 3 | High | Admin | Advertisments on the website | I can make money off the website |  | Displays ads |  |  | Open
|  |  | Currency |  | 1 | Med | Player | to be able to raise stakes of table | I can make more "fake" currency |  | Can set currency for table |  |  | Open
| this is part of the create story |  | Currency Given |  | 1 | High | Player | to start with currency when I make account/guest | I can play at tables |  | When account is made I have currency |  |  | Open
| I don't grok this one |  | Claim Currency |  | 1 | High | Player | to collect currency every 24 hrs in case I lose it all | I can continue to play if I lose |  | When I can collect currency every 24 hours |  |  | Open
| As the host? |  | Start game |  | 3 | High | Player | To start the game | I can play the game |  | When I am able to successfully start the game
R5? | something is wrong here |  | Round End | Start game | 5 | High | Player | When the round ends | I can see whether I won or lost |  | When the round ends after gameplay
R5 | how does this predict you likelihood of winning? |  | Check % | Start game | 2 | Med/High | Player | Toggle display of my winning % | I can see my chance of winning/losing |  | Winning percentage is shown when toggled
R5 | needs better expression of the value brought back to the user |  | Bot | Start game | 5 | Med | Player | Play with bot | I can play the game with a bot |  | When bot plays the game with player
R3 | admin user functions missing

## Tasks
ID | Task Title | Task Description | Story ID

## Epics
ID | Epic Title | Description